A collaborative approach to creating information literacy eLearning modules for the healthcare workforce

Final Report

December 2018

Michelle Maden (MM)
Tracey Pratchett (TP)
Sarah Lewis (SL)

# 1. Project Overview
## 1.1 Introduction
The Service Transformation eLearning Project (STEP) created freely available, generically branded eLearning modules aimed at developing literature searching skills among healthcare professionals in England. These short information literacy eLearning modules were created on a range of general topics that healthcare staff could complete flexibly. They are available via a central platform (eLearning for Healthcare (eLfH) https://www.e-lfh.org.uk/programmes/literature-searching/) for users to complete at their own pace and at a convenient time.
## 1.2 Project Rationale
This eLearning project arose from difficulties accessing face-to-face training delivered by NHS library services and a lack of freely accessible literature searching eLearning training. An evaluation of a Massive Open Online Course (MOOC) to train librarians in literature searching found that library staff wanted a similar course aimed at users of NHS library services (Maden et al., 2016). A review of existing eLearning found that resources were not generic enough and were often password protected.
The STEP project aimed to provide nationally available eLearning modules created using the guiding principles and values of the Knowledge for Healthcare Development Framework including collaboration and “do once and share” methodologies (Health Education England, 2015). The intention was to:
- Extend the reach of library services for those who find it difficult to access physical libraries
- Provide equitable access to training for staff who may not otherwise be able to attend face to face sessions
- Align library services with technology enhanced learning initiatives
- Deliver economies of scale by reducing the need for libraries to each produce their own eLearning programmes
- Harnessing specialist skills which may not be available at local level
## 1.2 Target Audience
The content was targeted at NHS healthcare staff wanting to learn how to conduct a literature search. The modules were developed for clinical and non-clinical staff to help build confidence and would be suitable for novice searchers and those wishing to refresh their knowledge. In addition, the content would be generic enough to be used by any library and knowledge service within NHS England, library staff working in the health academic sector or library staff working in health from outside England. Library staff would be encouraged to incorporate the content into existing local training programmes.

## 1.3 Project Team
A project team was established comprising the following members:
Project Leads
- Tracey Pratchett Knowledge & Library Services Manager at Lancashire Teaching Hospitals NHS Foundation Trust.
- Sarah Lewis, Library & Knowledge Services Manager at Buckinghamshire Healthcare NHS Trust.
Content developers
- Michelle Maden, Independent Clinical Information Specialist – Content developer.
- Blended Learning Team, Lancashire Teaching Hospitals NHS Trust, Mandy Davis, Blended Learning Manager and Wayne Troake, Senior Educational Technologist – eLearning developers.
User representative
Tracey Geddis an Advanced Nurse Practitioner from Buckinghamshire Healthcare NHS Trust - provided a healthcare professionals perspective.
## 1.4 Funding
The project was awarded £30,000 Health Education England.

# 2. Consultation process
In developing the eLearning, the dispersed project team consulted with a wide range of stakeholders. Consultation helped to prioritise the eLearning content, to avoid eLearning fatigue, to explore how to encourage use by healthcare staff and to encourage library staff to promote the eLearning.
## 2.1 Steering Group
The project was assimilated into the NHS Knowledge for Healthcare programme (Service Transformation work stream) and was overseen by a Steering group which provided accountability and guidance (Appendix 1). The Steering group helped to provide strategic direction, support project leads, link to other projects and raise awareness of STEP nationally. It included 12 representatives from different Health Education England Regions, the academic sector, public health and NICE. It met bi-monthly via Webex and was chaired by Helen Bingham, Head of Knowledge Services and Technology Enhanced Learning in the South.
## 2.2 Virtual Reference Group
The Virtual Reference Group (VRG) provided advice on the development of the eLearning modules. It included approximately 42 library staff that were referred by the Steering group or volunteered through the pre-development survey (see 3.1.2). The VRG represented Scotland, Wales and all Health Education England regions; and included library staff from across various health sectors e.g. acute, community, mental health, public health and hospices and from Universities, the Royal Colleges and NICE.

“I feel the STEP team strikes the right level of involvement required from the virtual reference group and gives members the option to be as involved as they wish/have time for. We've had quite detailed discussions about planning the module content and titles, then the team have gone away and produced a great first draft module.”

Yammer, an online sharing tool, was used to communicate and share resources with the VRG as it was one of the few platforms accessible across all organisations. They advised on developing the module content and tested the draft modules. They identified relevant search topics, commented on module design, debated the use of audio, influenced the animation design and championed the STEP project to their colleagues and healthcare staff. The VRG was crucial in producing a resource that was relevant and practical to the target audience and therefore, in increasing the impact and usage of the eLearning modules. A survey conducted in May 2017 (11 responses) indicated that the VRG felt they had the right level of involvement and enjoyed being part of the project.
## 2.3 Dissemination
The project leads communicated with the wider health library community in a number of ways, depending upon what needed to be shared:
- Project updates sent via email distribution lists e.g. LIS-MEDICAL@JISCMAIL.AC.UK.
- Regular updates to Steering Group in accordance with Knowledge for Healthcare programme.
- Posts on the Knowledge for Healthcare blog (http://kfh.libraryservices.nhs.uk/tag/service-transformation-eLearning-project-step/).
- Consultation with the Virtual Reference Group via Yammer and email.
- Project status communicated to regional library meetings across NHS England to engage stakeholders.
- Dissemination of learning via Health Libraries Group (HLG), Health Information Libraries Journal (HILJ) etc., to inform future projects.
- Presented at a number of national and international conferences: LILAC (2016), EAHIL (2016) and HLG (2018).
- Published in the Health Libraries Group newsletter.

# 3. Module Development
Module content, titles, learning objectives and design were developed in consultation with library staff and healthcare staff based on the results of an initial survey (see below 3.1.2). Input was also sought from the Steering group and the VRG. Module content was led by MM, with guidance from the two project leads TP, SL. Module design was led by the project team with input from the VRG and Steering Group.
## 3.1 Content development process
Consultation with librarians and healthcare professionals was essential to ensure the modules met the needs of healthcare staff working in a variety of settings. A short scoping survey of clinical staff and library staff in NHS England was undertaken to prioritise content for the eLearning and to understand how the modules could be used. Given the difficulties facing NHS organisations in getting everyone through the statutory and mandatory eLearning modules the survey also aimed to identify the barriers and facilitators to using eLearning.
### 3.1.2 Pre-development survey
Surveys were conducted with library staff and the healthcare workforce to identify what the modules should focus on and influence module design. The surveys highlighted the needs of both groups and factors most likely to encourage or inhibit the use of eLearning. The results revealed interesting differences between the perceptions of healthcare staff and library staff about information literacy needs. The full results of the survey can be found on the Knowledge for Healthcare Blog (Pratchett, T & Lewis, S, 2016).
Survey respondents
139 library staff and 173 healthcare workforce responded to the survey. Although the sample size represented a small proportion of the total healthcare workforce, all core groups were well represented.
Survey recommendations
The structure and design of the modules should be:
  - Short
  - Interactive
  - Clear and easy to follow
  - Easily accessible preferably without logins
The content should focus on:
- Literature searching at an introductory level
- Refining the search (too many or too few results)
- Accessing full text articles
- Raising awareness of different resources
These principles were at the forefront of planning the overall design and content of each of the eLearning modules.
## 3.2. Module development process
Learning objectives were developed in consultation with the Steering group and VRG. To provide consistency, a template was used to develop the training scripts (MM) for each module, which were reviewed by the project leads (TP,SL) before they were sent to the Blended Learning Team (WT) for translation into an online format. Once drafted, the modules were shared with the Steering group and VRG for final comment, testing and evaluation. Modules were rigorously tested by the eLfH team to ensure compatibility with their online platform and a range of browsers and devices.
## 3.3 Overview of modules
The seven modules were split into three groupings; building the foundations, developing the skills and applying the skills. Table 1 outlines the content within each of the seven modules. The modules focus on skills development and behaviour change, rather than using a specific database platform. The exception to this is the final ‘How to search the Healthcare Databases (HDAS)’ module, which encourages people to try out the skills they have learnt on a key platform developed by NICE for the NHS. Learning objectives were developed for each module and mapped to the health version of the 7 SCONUL Pillars of Information Literacy (Dalton, 2013). The full learning objectives for each module can be viewed on the eLfH web site https://www.e-lfh.org.uk/programmes/literature-searching/
Table 1: STEP module content
Building the foundations
Introduction to the modules	This module provides an overview of the searching process and its main purpose is to get the user to think about their current level of knowledge.	Behaviour change: Know where to get help with searching / SCONUL Pillars: Identify; Scope;
Where do I start searching?	This module aims to help the user look in the right places for information based on the topic and the type of information required.	Behaviour change: Use the right resources to save time searching / SCONUL Pillars: Scope; Gather; Evaluate
How do I start to develop a search strategy?	This module aims to show the user the benefits of planning a search strategy using tools such as PICO and 4Ws as well as identifying keywords and synonyms.	Behaviour change: Put time into planning the search to get the most out of it / SCONUL Pillars: Identify; Plan

Developing the skills
Too many results? Narrowing your search strategy	This module provides an overview of key search techniques to reduce the number of results.	Behaviour change: Not give up on searching because you find too much information / SCONUL Pillars: Plan
Too few results? Broadening your search strategy	This module provides an overview of key search techniques to increase the number of results.	Behaviour change: Not give up on searching too soon because you don’t find much information / SCONUL Pillars: Plan
Searching with subject headings	This module is aimed at those who already know some of the basics of searching but aren’t confident in using the thesaurus.	Behaviour change: Applying more advanced search techniques / SCONUL Pillars: Plan

Applying the skills
How to search the Healthcare Databases (HDAS)	This module is useful for those who want practice going through the process of a searching a database from start to finish.	Behaviour change: Apply a range of search techniques to an essential resource for the healthcare workforce / SCONUL Pillars: Plan; Gather

## 3.4 Module design
STEP aimed to produce a package which is visually appealing and uses simple, creative explanations for learning key concepts. The modules were created using Articulate Storyline and were designed according to the Health Education England branding guidelines (Health Education England, 2016).
### 3.4.1 Module formats

Figure 1 Interactive activity example
Multiple formats were embedded within the eLearning to appeal to different learning styles. Each module was constructed to maximise interactivity, by enabling the learner to complete exercises and assessments which test their learning against the learning outcomes (see figures 1). Each module has a downloadable resources handout summarising key learning points. Users are also able to download a certificate on completion to support CPD.
### 3.4.2 Module structure
The project team adopted a blended learning approach so that the modules, or elements of the modules, can be used flexibly by library staff to support their training. Reusable learning objects (RLOs) were embedded within the modules. RLOs are available via You Tube so that library staff can embed them as a standalone objects in their website , own eLearning products and use them within teaching sessions:
- AND/OR https://www.youtube.com/watch?v=N258crAefSo
- AND https://www.youtube.com/watch?v=yS2hHNR8pmo
- OR https://www.youtube.com/watch?v=xQDkIeNPrnc

Modules were designed so that they were short, taking no more than 20 minutes to complete and are structured so that each module can be “dipped into” for or completed in full during one session.
### 3.4.3 Accessibility
The modules were tested using a colour contrast check (Snook, 2005) to ensure that the colours were compliant with W3C accessibility guidelines (W3C, 2018). As the orange colours used in the Health Education England branding guidelines (Health Education England, 2016) were problematic for some people, an accessibility option to change the module colour scheme was provided which could be switched on as required. There is very little audio throughout the modules and the AND/OR animations are available with subtitles. No login is required to improve access to the modules as identified by the pre-development survey. However if a user wishes to track their learning along with other modules within eLfH, they can login to the web site.
### 3.4.4 Hosting platform & technical requirements
The eLearning is hosted centrally on an HEE server, and is freely available via the eLfH website (https://www.e-lfh.org.uk/programmes/literature-searching/) with web-links available for embedding on local websites. The source files will also be added to the NHS eLearning Repository (National Library for Health, 2008) so that they can be downloaded and used within local learning management systems. All modules were tested on a variety of devices and browsers by the eLfH team. The modules work best with an ‘HTML 5 compatible browser’.
# 4 Module Evaluation
A purpose built survey was embedded at the end of each module to capture feedback from all users. Some users chose to login to the eLfH platform, which provided some data about user demographics and additional feedback. It is difficult to assess the cost-effectiveness of the modules as we cannot obtain accurate usage data due to the removal of the need to login. However, based on the current usage to date, the modules appear to provide good return on investment. We have combined the data from these sources extracted on 8th October 2018 to evaluate the success of the project.
## 4.1 Total usage
The eLearning for Healthcare hub recorded 3679 sessions across all seven modules. It is not known how many additional sessions took place without a login. There were a total of 317 responses to the Survey Monkey evaluation which did not require end users to be logged into the eLfH hub.
### 4.1.2 Module usage
Table 2: Number of logged in sessions and Survey responses
Module	Date of module launch	No of sessions logged in eLfH	No of responses to Survey Monkey
Module 1	Nov 2017	1240	197
Module 2	Nov 2017	704	46
Module 3	Nov 2017	712	29
Module 4	Feb 2018	346	19
Module 5	Feb 2018	281	6
Module 6	Feb 2018	289	10
Module 7	Aug 2018	107	10
Total		3679	317

The modules were launched in phases and it is not surprising that Modules 1-3 were the most heavily used with Module 7 being the least used. This pattern is mirrored in the evaluation survey with Module 1 receiving the majority of feedback (197) and modules launched in the second and third phases receiving fewer responses.

Number of responders
## 4.2 User Profile
According to data from eLH, the seven modules were used by 811 individuals. The profile of these users is broken down as follows:

Table 3: Location
Location	Number
NHS England	682
Rest of UK	15
International	34
Unknown	80

Table 4: Organisation type

Organisation Type	Number
NHS Trusts (including mental health and community)	351
Other / unknown	351
University	56
Primary care / health centres	14
Public health / local council	11
CCG/ Health Board	8
Hospice	8
Pharmacies / Medicines Information	2
Health Education England	2
Ambulance Trusts	2
Care home	1
NHS England	1
NHS Education Scotland	1
NICE	1
Public library	1
Healthwatch	1

Table 5: Job role

Job Role	Number
Students	232
Library Staff	191
Other / unknown	78
Medical and dental	74
Allied health professionals	55
Nursing, midwifery and health visitors	42
Educators	34
Admin and clerical (excluding library staff)	24
Technical and scientific healthcare staff	22
Healthcare assistants, support workers, associate practitioners (including social care)	17
Managers	17
Public health	7
Patients and public	2

The Survey Monkey feedback also included a question about job role. The highest proportion of responses (31%) came from those in an admin or clerical role. Based on the nature of the comments given, the majority of these appear to be library staff testing the modules before promoting to their end users. 44 out of the 55 who selected the category ‘Other’ were also library staff. Among healthcare groups, students (15%), nurses (14%) and medical and dental staff (10%) were the highest number of respondents.
## 4.3 Module evaluation
When logged into eLfH, people are routinely asked to rate each module out of 5 to assess the quality of content, presentation, interactivity and self-assessment. 171 respondents rated the modules on the eLfH platform. All modules scored over 4 out of 5 on average, which shows that the modules were well received by users. Most responses (44%) were received for Module 1 with Module 7 receiving only 3 responses (2%). Overall, presentation was the highest rated element across all seven modules. There were no major concerns with the modules, and no comments were made which could be used to inform improvements.
### 4.3.1 Feedback survey
The embedded survey collected quantitative and qualitative data to assess the suitability of the content, its impact on learning and the overall design. Learners were given the opportunity to provide further comments, which are analysed below and will form the basis of our recommendations for developing the content and producing future eLearning.

Do you think the information provided was suitable for your needs?
The majority of responders (89%) felt that the modules were suitable for their needs. 8% felt that the modules were too basic and 3% felt that they were too complex.
Did this module help you learn what you needed to know?
79% of responders felt that the module helped them to learn what they needed to know, or mostly what they needed. 19% felt that they learned some of what they needed to know, whilst only 2.5% said they learned nothing new.
How did this module help your learning about literature searching?
Most responders (61%) felt that the module evaluated help to confirm prior knowledge and 43% felt they had gained new knowledge and/or new skills. Over a quarter of all responders (27%) said that the module had helped improve their confidence. Very few responders (3%) felt that the module made no difference. Most of those who chose the option ‘Other’ said they had used the module to test with their library users so hadn’t anticipated learning anything new.

Figure 2: How did this help your learning?

How would you rate the following aspects (i.e. the length, content, interactive exercises, navigation) of the module?
The majority of respondents rated the length of the module, content, interactive exercises and navigation as either good or excellent (see table 6). Interactive exercises were more likely to receive a Poor rating but this was still low at around 2.5%.
Table 6: Rating of length of module, content, interactive exercises, navigation
	Poor	Average	Good	Excellent
Length of module	0%	6%	63%	31%
Content	1%	10%	61%	28%
Interactivity	3%	9%	53%	35%
Navigation	1%	5%	54%	40%

Overall, how useful did you find this module?
55% percent of responders found the module they evaluated extremely useful. 44% percent felt it was somewhat useful, while only two percent said it wasn’t useful.
How did you find out about these eLearning modules?
Users heard about the modules from the eLfH website (26%) or via their local library website/service (24%). 19% came across the modules via a university library service / website and 15% were recommended the resource from a colleague, 3% through social media and 1% from a search engine. Other methods reported include; intranets, conferences, knowledge networks, email discussion lists, newsletters, Knowledge for Healthcare blog and recommendations from university lecturers.

“New knowledge I had no idea about, thank you very much for the knowledge shared. will help me improve my practice and gain confidence in my practice as a radiographer”
Additional comments
Comments received from the survey provide richer detail about the learning experience (Appendix 2). General comments suggest that learners found the modules extremely useful and they fulfilled the purpose of providing accessible eLearning. Others stated that they had picked up new skills and knowledge, whilst some felt that it was a good refresher.
It also is encouraging to see that some librarians found the modules useful and will embed them in their training, fulfilling our aim to deliver eLearning that could become part of a blended training offer.
“Really good module, I was doing it to use it as part of a blended learning approach for a group of occupational therapists who are coming to attend a training session within our library in a few weeks’ time.”
A number of comments received from the evaluation highlight some recurrent themes which need further exploration. These are summarised below and will form the basis of recommendations for revision of the products.
Technological issues
Four users reported challenges with on screen formatting, missing letters, problems with interactive exercises and blocked web sites. The modules were tested on a range of devices and browsers by the eLfH team and it appears that these issues are sporadic and may be linked to local settings. Where learners have contacted the project team directly, we have tried to troubleshoot these issues. Vimeo and YouTube are used to host video content, but these are blocked by some organisations unfortunately.
Navigation
Three learners found the navigation unclear and able to move on too quickly. One learner found the prompts in Module 1 confusing as they felt that the prompts suggested they had moved onto a different module.

Accessing the module
Although there is no need to login to the modules, some people found it challenging to register on the platform. This feedback will be forwarded to the eLfH team for investigation.
Module content
Two users commented on the content of Module 3 indicating that the funnel interactive exercise was confusing and that the PICO example used included some incorrect wording. It was also suggested that examples of the alternatives to PICO should be included. Five comments discussed the content of Module 1 and a number of these were submitted by librarians. Some of the confusion lay in the purpose of the module as some librarians felt that the assessment was asking questions that had not been covered. The module was devised as an initial assessment to help learners’ focus on the areas they need to develop. One user suggested that it didn’t explain Medline, Cinahl etc, but these are covered in Module 2. There may need to be some further promotion around the purpose of this module for librarians.
### 4.3.2 Module Evaluation Summary
Overall, user feedback on the STEP project was positive and is encouraging. The content was well received and feedback suggests that it was pitched at the right level for the audience. It is encouraging to note that 98% of users reported that the modules improved their learning. Furthermore, 97% felt that the modules confirmed prior knowledge or provided new knowledge, updated their skills, or improved their confidence in literature searching. Based on the initial evaluation, STEP appears to have achieved its aims in providing eLearning to help both clinical and non-clinical staff build confidence in conducting literature searches.Additionally, initial feedback indicates that librarians are planning to integrate them into their training programmes.
As expected a small number of technological issues arose, relating to accessing videos, responsiveness of the technology and the appearance of text. These access issues applied to a minority reflecting the great variability in IT systems across the NHS. Furthermore, the STEP modules are available 24/7 so that participants can access the resources from outside their organisations if desired. Some users found registering for the eLearning problematic. This is out of the control of the project team but will be fed back to the eLfH team for investigation.
The survey responses mainly relate to Module 1, ‘Introduction to searching’ (67%). This module is different to the other modules as it aims to assess current levels of searching knowledge and provide an overview of the following modules. The survey does not assess whether literature searching skills and confidence of users improved as they progress through the modules as users do not need to complete all modules. It is also difficult to judge how much knowledge, skills and confidence improved across the different modules using an online survey. Furthermore, the fact that the number of completed evaluations drop as the modules progress could indicate ‘evaluation fatigue’.
From the comments received we suspect that a large proportion of the feedback has come from library staff who were testing or evaluating the modules prior to dissemination to their library users. The target audience for the eLearning in terms of improving literature searching skills and confidence are non-librarians and novice searchers. A more focussed evaluation of the modules at a later date may provide responses more representative of the target end-user audience. The responses represent a small proportion of the NHS workforce and we do not have data on non-responders. Therefore we cannot currently comment on the reasons that healthcare professionals are not accessing the STEP modules.

# 5 Process evaluation
A project on this scale with the aim of appealing to a broad audience was not without its challenges. In outlining some of these challenges, the project team share their reflections and recommendations for taking forward similar projects. Lessons learned along the way can also be read on the Knowledge for Healthcare blog (http://kfh.libraryservices.nhs.uk/8-eLearning-lessons-we-learnt-the-hard-way/).
### 5.1 Project management
Managing a large scale project like this was challenging and timescales slipped due to unforeseen circumstances. Unanticipated changes to the development team when someone left meant we had to start building a new relationship and revisit our design ideas. This challenged our ability to meet our original deadlines, as did annual leave and other priorities among team members. Setting clear deadlines was always going to be challenging when staff take on projects like this on top of existing roles and responsibilities.
### 5.2 Having a dispersed team
It was challenging having project leads at opposite ends of the country, having a dispersed project team, Steering Group and VRG. Most of our meetings were held virtually and this added to time delays. Yammer was chosen as a platform for sharing files as it seemed to be accessible to most with few exceptions. However, problems in access were encountered as Trusts switched over to NHS.net during the project. In addition, some feedback from the VRG indicated that Yammer was ‘clunky’, difficult to navigate and challenging to engage with.
### 5.3 Writing eLearning content
Three of the project team (TP,SL,MM) are experienced trainers who are used to writing training materials. However, effective eLearning is very different from writing a MOOC or a usual training session. It is not enough to simply translate existing materials into an online format in order to fulfil objectives. ELearning needs to be succinct, visual, interactive and meet varied learning needs.
It is difficult to determine how much detail is required for explanations; too much and it will make the screen too busy and confusing. Without face to face contact, the trainer isn’t on hand to give explanations if someone doesn’t understand the terms being used, so there is a need to be clear from the outset. It can also be difficult to gage if people are losing interest or don’t fully understand. A glossary and handouts can be helpful to provide more information. Interactive exercises are more engaging but complicated activities can be difficult to produce.
A lot of time was spent reworking scripts and collating comments and some inconsistencies emerged in the terminology used across the 7 modules. Partway through the project, we introduced a standard template which sped up the process and made it easier to collate changes. Using a standard template helps maintain a consistent format across a range of modules.
### 5.4. Creating a product to meet all needs
The scale of the consultation made it difficult to produce eLearning that would suit all needs. The STEP materials were based on feedback from clinical staff, the wider workforce and librarians who would be using the eLearning. This aimed to ensure that the product was relevant and ‘fit for purpose’. It was difficult to reach everybody, but a wide range of stakeholders engaged with the project. However, receiving input from varied stakeholders made it difficult to produce a ‘generic’ product to appeal to all. The project team had to make decisions on the content that may not have suited everyone.
It was difficult to know when to stop consulting and it took a long time to sign off the first modules. It was important to learn when to stop and accept that it was good enough and have more confidence that the extensive consultation meant that we were developing what people wanted. Finally, it was difficult to please everyone, so compromises were made along the way.
### 5.5. Hosting eLearning in the NHS
A lot of consideration was given to where the resources would be hosted as there was no central space for general resources to sit for NHS Libraries. It was decided partway through the project that the eLfH platform would be the best place to host the content and testing started once the first modules were ready to go live. It was at this stage that a number of technical issues were identified which delayed the launch of the modules. With hindsight, the eLfH team should have been included within the project team from the outset, as their expertise and earlier input could have mitigated delays.
### 5.6 Evaluation tools
There are some limitations to the evaluation data presented in this report. In order to make the modules accessible, we had to forego making users’ login to the eLfH platform which means that usage data is limited. The embedded survey does not provide a balanced picture of all modules and this may have skewed the overall results. It also may have been useful to have an individual survey for each module, which focussed on the areas that the module covered, rather than use general questions. As we do not know how many people have accessed the modules, we don’t know what proportion chose to complete the survey. Also it is worth noting that the modules were created for users to dip in and out of, so they may not reach the survey at the end of the module. The survey also assessed current learning, but has failed to establish whether the modules have really helped to improve learning in the longer term.

# 6. Summary and conclusions
The STEP project was designed to develop freely available, generically branded eLearning modules aimed at developing literature searching skills among NHS healthcare professionals in England. The STEP modules are available 24/7 for all library services to use as part of their blended training offer and are hosted on a national eLearning platform which does not require a login. Feedback from an initial evaluation suggests that STEP appears to have achieved its aims in providing a platform on which to help both clinical and non-clinical staff build confidence in conducting literature searches. Furthermore, initial feedback indicates that librarians are planning to integrate them into literature searching training sessions.

This ambitious project demonstrates the importance of collaborative working. Throughout all stages of the project engagement and consultation with stakeholders has been sought, initially via the survey and then ongoing through the VRG, Steering group and the clinician on the project team. This aimed to ensure that the final product was relevant and ‘fit for purpose’. Bringing experts together from across different areas has enabled the delivery of a suite of resources which aims to change the way that NHS librarians deliver literature searching training across the country. By working together, obtaining funding from HEE and employing specialists, a higher quality product was created than they could have developed independently. The project team make a series of recommendations to improve the products and based on feedback and also aim to help others identify potential risks at the start of similar projects with a view to mitigating these.
# 7. Recommendations
Based on the above evaluations and reflections on the STEP project the following recommendations are presented:
### 7.1 Recommendations for the project team
Based on this evaluation, the project team will take forward the following actions:
Promotion and awareness raising:
- Encourage library staff to use the modules
- Explain the use and purpose of module 1
- Advise that there is no need to login to eLfH
- Publish a series of blog posts “Getting the most out of STEP”
- Submit “STEP – 1 Year on” to the HLG Newsletter
- Facilitate a workshop at the Northern Conference “Embedding eLearning into training
Evaluation:
- Conduct evaluation at a later date with a focus group
- Work with Knowledge Mobilisation Framework eLearning leads to establish the use/impact of eLearning
- Publish the project findings in Health Information Libraries Journal
Technical Difficulties:
Share solutions to some of the known technical hitches
Add text to eLfH homepage advising that embedded videos may be blocked by individual trusts
Content review:
- Review modules 1, 2 and 3
- Share in the eLearning Repository for local LMS or adaption
  1. Recommendations for people managing similar projects
Content development:
- Involve stakeholders in content development
- Develop a clear process and stick to it
Writing eLearning content:
- Be consistent in use of language
- Avoid jargon
- Minimise text
- Involve a learning technologist
- Interactivity is important, but don’t over complicate
- Version control any scripts
- Collate comments to send to online developers
Creating a product to ‘meet all needs’:
- Involve stakeholders throughout the whole process
- Don’t be afraid to take the final decision on what content to include and when to stop consulting, but ensure you can justify your decisions
Hosting eLearning in the NHS:
- Establish the external host sooner
- Embed a member of the hosting team in the project team
- Ask more questions of the host about testing, evaluation and timescales
Project management:
- Review milestones
- Build in time for unforeseen circumstances
- Take a long term view
- Use formal project management tools
- Account for annual leave and other commitments
- Set clear deadlines
Having a dispersed team:
- Find a sharing tool that works for most people – our experience suggests not Yammer
- Have regular telephone meetings
- Schedule in some face-to-face meetings
- Make sure you have regular meetings pencilled in ahead can help keep the momentum going

# 9. References
Tweddle, L. (2008) Time out for training. Nursing Times. 104 (2), p20-23.
Maden, M., Young G., McLaren L. (2016). The LIHNN Introduction to Literature Searching MOOC. Final Report. Available at: https://lihnnclinicallibs.files.wordpress.com/2017/04/lihnn_mooc_evaluation_report_revj16.pdf Date accessed 22.10.2018
###### Labour Research Department. (2015) RCN Employment Survey 2015. London: Royal College of Nursing.
Lewis, S., Pratchett, T. (2017) 8 e-learning lessons we learnt the hard way. Available at: https://kfh.libraryservices.nhs.uk/8-e-learning-lessons-we-learnt-the-hard-way/ Date accessed 22.10.2018
Health Education England (2015) Knowledge for Healthcare: A development framework. Available at: https://kfh.libraryservices.nhs.uk/wp-content/uploads/2018/03/Knowledge_for_healthcare_a_development_framework_2014.pdf Date accessed 22.10.2018
Pratchett, T., Lewis, S., (2016) Different folks, different strokes: results of the STEP E-learning surveys. Available at: https://kfh.libraryservices.nhs.uk/different-folks-different-strokes-results-of-the-step-e-learning-surveys-by-tracey-pratchett-and-sarah-lewis/ Date accessed 22.10.2018
ELearning for Healthcare. (2018) How to search the literature effectively. Available at: https://www.e-lfh.org.uk/programmes/literature-searching/ Date accessed 22.10.2018
Dalton, M. (2013) Developing an evidence-based practice healthcare lens for the SCONUL Seven Pillars of Information Literacy model. Journal of Information Literacy, 7(1), p. 30-43 Available at: https://ojs.lboro.ac.uk/JIL/article/view/PRA-V7-I1-2013-3/1811 Date accessed 7.11.2018
Health Education England. (2016) Corporate identity guide. London: Health Education England.
National Library for Health. (2008) NHS eLearning Repository. Available at: https://www.elearningrepository.nhs.uk/ Date accessed 7.11.2018
# Appendix 1 Steering Group Terms of Reference

Appendix 2 Comments from the survey
On screen formatting	“for some reason the letter "f" and a few letter "i"s were missing from the text in the module. This may have been due to issues with the browser on my old NHS computer, but it made it more challenging to read the text.”
	“Problems with the drag and drop functions. Selected the correct answers but wasn't recognised.”
Technology issues	“freezes on last page, had to skip it.”
	“The interactive exercises and navigation buttons weren't very responsive and the last interactive activity repeatedly crashed the session.”
Navigation	“To start with, navigation was a little unclear - especially re what parts of the screen to click on as they weren't obvious buttons (apart from the 'next' button)”
	Sometimes the reminders to the other modules were confusing and I wasn't sure whether I was / still only on the first module or if I'd moved on
	I had to keep on using the menu/index to resume my previous position after finding that I had / moved on a screen too early.
Blocked websites	“unfortunately there were some websites shown as 'blocked' due to restrictions in our work place. eg. Video.”
	Unfortunately Vimeo is currently blocked locally. I have submitted a request to get it unblocked but / this is a major issue for this module. Is there nowhere we can host this that is definitely NHS / acceptable? Could nhs.uk provide us a bit of space or some other site that is definitely whitelisted?
Accessing the module	“Registering for the module was the hardest part of the process as the content and adjustability of drop down menus are very poor.”
Content	In the PICO example, it was a bit confusing that "fever" was stated as an Outcome in some places instead of "reducing fever". Also, it would have been helpful if the page of alternatives to PICO had included examples of situations where they would be relevant.
Interactive exercises	The funnel exercise was a little confusing at first as I was expecting an animation to move the / choices down. I ended up throwing in a choice and clicking 'next' to confirm if it was actually / working or not.
Module one content	“I am an nhs librarian who teaches information skills training. I think as a first module for beginners it may put people off. For example it covered ways to narrow a search such as restricting to title only. However the question then asked how you narrow a search. As an experienced searcher I knew you would choose title searching, applying limits and phrase searching so I got answer correct. However if you had only chosen title searching you would have got an incorrect answer. as limits etc had not been covered in first module it seems unfair to mark people down and ask questions which have not been properly covered in module.” / “Doesn't explain what the different areas to search were eg Medline, cinahl etc.” / “I was testing this for someone who had no previous knowledge. I felt that they could not be expected to know some of the answers and had not been given information to allow them to work it out.” / “Sometimes the reminders to the other modules were confusing and I wasn't sure whether I was still only on the first module or if I'd moved on.” / “Some prior knowledge of databases is needed so could throw a beginner.”

General comments	“effective search of the databases is a highly-taxing stage for the postgraduate researchers and students. from my perspective, this is the best and the simplest course I have ever had. great work and big thanks”
	“Highly interactive module and worth many courses and videos I have taken and watched so far.”
	“Most helpful for a newbie. Thanks.”
	“Excellent way to learn”
	“the best tutorial ever!”
Knowledge and skills	Many thanks for this module. I thought it would really be a case of only refreshing skills and knowledge that I already had but I did pick up some useful hints and tips to improve my searching on HDAS.
	“new knowledge i had no idea about, thank you very much for the knowledge shared. will help me improve my practice and gain confidence in my practice as a radiographer”
	“Useful module for beginner's or those seeking to refresh their memory on introductory literature searching skills.”
Teaching others	“Will be using it to signpost staff towards if they want to try eLearning rather than contacting library training staff”
	“Really good module, I was doing it to use it as part of a blended learning approach for a group of occupational therapists who are coming to attend a training session within our library in a few weeks’ time.”
	“I am a healthcare librarian and wanted to see what these modules contained. I think it would be very useful as a basic introduction - thanks!”
	“I'm always going to be biased toward training using a real, live person, as I can make training more personalised & answer questions, but this was pretty good - should be useful for situations where staff can't arrange a session with us, or want to try & get to grips with lit searching on their own - well done & roll on the other modules!”
	Handy for promoting evidence searching skills to our library users