## Sheet1
Resource Discovery Timelines
Elements | Specifics | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01
Authentication | 2018-2022 OpenAthens contract | bar: 2021-09-01 to 2023-03-01
Authentication | 2022-2024 OpenAthens contract | bar: 2021-09-01 to 2023-03-01
Move to provider databases | Training to use provider database interfaces by providers | bar: 2021-09-01 to 2023-03-01
Move to provider databases | Provider database training with KLS expert searchers - phase 1 | bar: 2021-09-01 to 2023-03-01
Move to provider databases | Provider database training with KLS expert searchers - phase 2 | bar: 2021-09-01 to 2021-10-01; 2022-01-01 to 2022-02-01
Move to provider databases | HDAS available | bar: 2021-09-01 to 2023-03-01
Move to provider databases | Provider databases used for evidence searches | bar: 2021-09-01 to 2023-03-01
Move to provider databases | Co-production of promotional and training collateral | bar: 2021-09-01 to 2023-03-01
Move to provider databases | Promotional collateral and training collateral available | bar: 2021-09-01 to 2023-03-01
Move to provider databases | Development of peer support activities | bar: 2021-09-01 to 2023-03-01
Move to provider databases | Peer support activities delivered | bar: 2021-09-01 to 2023-03-01
NHS Knowledge and Library Hub | Setup of EDS instances | bar: 2021-09-01 to 2023-03-01
NHS Knowledge and Library Hub | Launch of NHS Knowledge and Library Hub | bar: 2021-09-01 to 2023-03-01
NHS Knowledge and Library Hub | Welcome to the NHS Knowledge and Library Hub training | bar: 2021-09-01 to 2023-03-01
NHS Knowledge and Library Hub | EBSCO Link resolver and EDS administration training | bar: 2021-09-01 to 2023-03-01
Link resolver | Wolters Kluwer/TDNet Link Resolver contract | bar: 2021-09-01 to 2023-03-01
Link resolver | Training on using EBSCO Link Resolver and Holdings Links Management | bar: 2021-09-01 to 2023-03-01
LibKey | Introduction to LibKey and BrowZine Workshop (North East and Yorkshire, national organisations, London, the East of England and the South East) | bar: 2021-09-01 to 2023-03-01
LibKey | Introduction to LibKey and BrowZine Workshop (South West) | bar: 2021-09-01 to 2023-03-01
LibKey | Introduction to LibKey and BrowZine Workshop (Midlands and the North West) | bar: 2021-11-01
LibKey | LibKey Advanced - Libkey.io and LibKey Nomad (North East and Yorkshire, national organisations, London, the East of England and the South East)
LibKey | LibKey Advanced - Libkey.io and LibKey Nomad (South West) | bar: 2021-11-01
LibKey | LibKey Advanced - Libkey.io and LibKey Nomad (Midlands and the North West) | bar: 2021-11-01 to 2021-12-01
LibKey | Advice on the implementation of LibKey Nomad to ICT published | bar: 2021-09-01 to 2023-03-01
LibKey | Setup of ThirdIron accounts to be able to administer LibKey instances | bar: 2021-09-01 to 2023-03-01
LibKey | Integration of LibKey with provider databases | bar: 2021-09-01 to 2023-03-01
Library Management Systems | East of England and KSS Consortia - procurement | bar: 2021-09-01 to 2023-03-01
Library Management Systems | East of England and KSS Consortia - implementation | bar: 2021-09-01 to 2023-03-01
Library Management Systems | Midlands Koha Consortium - phase 1a | bar: 2021-09-01 to 2023-03-01
Library Management Systems | Midlands Koha Consortium - phase 1b | bar: 2021-09-01 to 2023-03-01
Library Management Systems | Midlands Koha Consortium - phase 2 | bar: 2021-09-01 to 2023-03-01
National Core Content | Current National Core Content contract | bar: 2021-09-01 to 2023-03-01
Helpdesk and support | Set up of FreshService helpdesk infrastructure | bar: 2021-09-01 to 2023-03-01
Helpdesk and support | Service desk open for routine business | N | Y+P49B49E49:O49E49:Q49E49:P49E4E49:Q49 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Helpdesk and support | Service desk open for enhacement and development requests | bar: 2021-09-01 to 2023-03-01
Helpdesk and support | Knowledgebase set up and populated with frequently asked questions | bar: 2021-09-01 to 2023-03-01
National KLS websites | Regional sites - content added to National Website Platform and National KLS website | bar: 2021-09-01 to 2023-03-01
Reference management tools | RefWorks accounts set up for KLS staff | bar: 2021-10-01 to 2023-03-01
Reference management tools | Training on using RefWorks | bar: 2021-09-01 to 2023-03-01